## Product Backlog
No | Function | Description
1 | Register | Registering to become member of website
2 | Login/Logout | Accessing the account to use their features
3 | Get forgotton password | Reseting password if forgetting
4 | Edit profile | Users edit their profile
5 | Create class | Teachers create class for student's joining
6 | Create article, question, answer | User post an article, ask a question or answer a question
7 | Upload material | Teachers upload their studying documents
8 | Invite teacher | Teachers invite other teachers to answer a question on
9 | Invite student | Teachers invite students to join the discussion in class
10 | Accept/Deny an invitation | Users accept/deny teachers' invitation
11 | Accept/Deny a request | Teachers accept/deny a joining request from student
12 | Track student | Teachers track students’ questions to see which topics a student is less known about
13 | Manage post | Users manage their post (edit, delete post)
14 | Manage class | Teachers manage students in their class
15 | Real time notify | System support real time notification when followed teachers have new posts or posts have new reply
16 | Real time discuss | New answers or replies will show at real time without refreshing page
17 | Manage learning materials | Students to create folders to store different kinds of studying documents
18 | Follow teacher | Students follow their favorite teachers
19 | Send a request | Students send a request to join in a teacher’s class.
20 | Suggest related post | System suggest related posts (related articles, related questions) for users
21 | Search | Users search posts or other users
22 | Manage users | Admin can ban/unban users
23 | Manage psots | Admin can remove posts

## Sprint 1
Sprint 1
No | Task | Detail information | Implementer | Estimated hours | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Design homepage |  | MinhKH | 10 | Completed |  |  |  |  | 5 | 5
2 | Design register page | Didn't submit | ThiTD | 6 | In process
3 | Design login form | Pop-up form, didn't submit | ThiTD | 6 | In process
4 | Design get forget password page | Didn't submit | ThiTD | 6 | In process
5 | Design student dashboard | Didn't meet deadline, didn't meet requirement | TungTD | 8 | In process
6 | Design teacher dashboard | Didn't meet deadline, didn't meet requirement | TungTD | 8 | In process
7 | Design admin dashboard | Didn't meet deadline, didn't meet requirement | TungTD | 8 | In process
8 | Report 1 | Didn't meet deadline | ThiTD | 4 | Completed
9 | Review report 1 |  | MinhKH | 3 | Completed | 3
10 | Setup environment turorial |  | KhangTN | 8 | Completed |  |  | 4 | 4
11 | Create overall use-case |  | KhangTN | 15 | Completed |  |  | 3 | 7 | 5
12 | Create guest use-cases | Start after KhangTN commits overall usecase, didn't submit | ThiTD | 10 | In process
13 | Create ERD |  | MinhKH | 12 | Completed |  |  | 6 | 6
14 | Create System Architectural Design |  | KhangTN | 10 | Completed |  |  |  |  | 5 | 5
15 | Report 2 | Didn't meet deadline | TungTD | 8 | Completed
16 | Review report 2 |  | MinhKH | 3 | Completed | [6 empty] | 3
17 | Review use-case, page design |  | MinhKH | 4 | Completed | [6 empty] | 4
Total estimated hours
| Implementer | Total hours
| MinhKH | 32
| KhangTN | 33
| ThiTD | 32
| TungTD | 32
Total actual hours
| Implementer | Total hours
MinhKH
KhangTN
ThiTD
TungTD
| Total task | 17
| Completed task | 10
| Not completed task | 7
| Implementer | Total task | Completed task | Performance
| MinhKH | 5 | 5 | 100%
| KhangTN | 3 | 3 | 100%
| ThiTD | 5 | 1 | 20%
| TungTD | 4 | 1 | 25%

## Sprint 2
| Sprint 2 |  |  |  |  | Start | 19/5 | End | 25/5
No | Task | Detail information | Implementer | Estimated hours | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Design class page |  | MinhKH | 12 | In process
2 | Design post page |  | MinhKH | 12 | New
3 | Design notification |  | KhangTN | 8 | New
4 | Design invitation |  | KhangTN | 8 | New
5 | Design teacher's profile viewer |  | TungTD | 8 | New
6 | Design student's profile viewer |  | TungTD | 8 | New
7 | Create guest use-case |  | ThiTD | 10 | New
8 | Create teacher use-case |  | KhangTN | 16 | New
9 | Create student use-case |  | TungTD | 16 | New
10 | Create admin use-case |  | ThiTD | 8 | New
11 | Create system use-case |  | ThiTD | 8 | New
12 | Create conceptual diagram |  | ThiTD | 6 | New
13 | Review use-case |  | MinhKH | 6 | New
14 | Review conceptual diagram |  | MinhKH | 4 | New
15 | Design register page | Sprint 1 task | ThiTD | 6 | In process
16 | Design login form | Sprint 1 task | ThiTD | 6 | In process
17 | Design get forget password page | Sprint 1 task | ThiTD | 6 | In process
18 | Design student dashboard | Sprint 1 task | TungTD | 8 | In process
19 | Design teacher dashboard | Sprint 1 task | TungTD | 8 | In process
20 | Design admin dashboard | Sprint 1 task | TungTD | 8 | In process
21 | Create guest use-cases | Sprint 1 task | ThiTD | 10 | In process
Total estimated hours
| Implementer | Total hours
| MinhKH | 34
| KhangTN | 32
| ThiTD | 60
| TungTD | 56
Total actual hours
| Implementer | Total hours
MinhKH
KhangTN
ThiTD
TungTD