## Product Backlog
No | Function | Description
1 | Register | Registering to become member of website
2 | Login/Logout | Accessing the account to use their features
3 | Get forgotton password | Reseting password if forgetting
4 | Edit profile | Users edit their profile
5 | Create class | Teachers create class for student's joining
6 | Create article, question | User post an article, ask a question
7 | Reply | Reply article or question
8 | Upload material | Teachers upload their studying documents
9 | Invite teacher | Teachers invite other teachers to answer a question on
10 | Invite student | Teachers invite students to join the discussion in class
11 | Accept/Deny an invitation | Users accept/deny teachers' invitation
12 | Accept/Deny a request | Teachers accept/deny a joining request from student
13 | Track student | Teachers track students’ questions to see which topics a student is less known about
14 | Manage post | Users manage their post (edit, delete post)
15 | Manage class | Teachers manage students, posts in their class
16 | Real time notify | System support real time notification when followed teachers have new posts or posts have new reply
17 | Real time discuss | New answers or replies will show at real time without refreshing page
18 | Manage learning materials | Students to create folders to store different kinds of studying documents
19 | Follow teacher | Students follow their favorite teachers
20 | Send a request | Students send a request to join in a teacher’s class.
21 | Suggest related post | System suggest related posts (related articles, related questions) for users
22 | Search | Users search posts or other users
23 | Manage users | Admin can ban/unban users
24 | Manage psots | Admin can remove posts

## Sprint 1
Sprint 1
No | Task | Detail information | Implementer | Estimated hours | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Design homepage |  | MinhKH | 10 | Completed |  |  |  |  | 5 | 5
2 | Design register page | Didn't submit | ThiTD | 6 | In process
3 | Design login form | Pop-up form, didn't submit | ThiTD | 6 | In process
4 | Design get forget password page | Didn't submit | ThiTD | 6 | In process
5 | Design student dashboard | Didn't meet deadline, didn't meet requirement | TungTD | 8 | In process
6 | Design teacher dashboard | Didn't meet deadline, didn't meet requirement | TungTD | 8 | In process
7 | Design admin dashboard | Didn't meet deadline, didn't meet requirement | TungTD | 8 | In process
8 | Report 1 | Didn't meet deadline | ThiTD | 4 | Completed
9 | Review report 1 |  | MinhKH | 3 | Completed | 3
10 | Setup environment turorial |  | KhangTN | 8 | Completed |  |  | 4 | 4
11 | Create overall use-case |  | KhangTN | 15 | Completed |  |  | 3 | 7 | 5
12 | Create guest use-cases | Start after KhangTN commits overall usecase, didn't submit | ThiTD | 10 | In process
13 | Create ERD |  | MinhKH | 12 | Completed |  |  | 6 | 6
14 | Create System Architectural Design |  | KhangTN | 10 | Completed |  |  |  |  | 5 | 5
15 | Report 2 | Didn't meet deadline | TungTD | 8 | Completed
16 | Review report 2 |  | MinhKH | 3 | Completed | [6 empty] | 3
17 | Review use-case, page design |  | MinhKH | 4 | Completed | [6 empty] | 4
Total estimated hours
| Implementer | Total hours
| MinhKH | 32
| KhangTN | 33
| ThiTD | 32
| TungTD | 32
Total actual hours
| Implementer | Total hours
MinhKH
KhangTN
ThiTD
TungTD
| Total task | 17
| Completed task | 10
| Not completed task | 7
| Implementer | Total task | Completed task | Performance
| MinhKH | 5 | 5 | 100%
| KhangTN | 3 | 3 | 100%
| ThiTD | 5 | 1 | 20%
| TungTD | 4 | 1 | 25%

## Sprint 2
| Sprint 2 |  |  |  |  | Start | 19/5 | End | 25/5
No | Task | Detail information | Implementer | Estimated hours | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Design class page |  | MinhKH | 12 | Completed | 10
2 | Design post page |  | MinhKH | 12 | Completed
3 | Design notification |  | KhangTN | 8 | Completed
4 | Design teacher's profile viewer | TungTD->MinhKH | TungTD | 8 | Completed
5 | Design student's profile viewer | TungTD->MinhKH | TungTD | 8 | Completed
6 | Design create class page |  | KhangTN | 10 | Completed
7 | Design create post page |  | KhangTN | 16 | Completed
8 | Design register page | Sprint 1 task (ThiTD -> MinhKH) | MinhKH | 6 | Completed
9 | Design login form | Sprint 1 task (ThiTD -> MinhKH) | MinhKH | 6 | Completed
10 | Design get forget password page | Sprint 1 task (ThiTD -> MinhKH) | MinhKH | 6 | Completed
11 | Design student dashboard | Sprint 1 task -> MinhKH | TungTD | 8 | Completed
12 | Design teacher dashboard | Sprint 1 task ->MinhKH | TungTD | 8 | Completed
13 | Design admin dashboard | Sprint 1 task | TungTD | 8 | In process
14 | Fix overall use-case |  | MinhKH | 1 | Completed
15 | Fix ERD |  | KhangTN | 2 | Completed
16 | Fix System architecture |  | KhangTN | 2 | Completed
Total estimated hours
| Implementer | Total hours
| MinhKH | 43
| KhangTN | 38
| TungTD | 40
Total actual hours
| Implementer | Total hours
MinhKH
KhangTN
TungTD
| Total task | 16
| Completed task | 15
| Not completed task | 1
| Implementer | Total task | Completed task | Performance
| MinhKH | 6 | 10 | 166.7%
| KhangTN | 5 | 5 | 100%
| TungTD | 5 | 0 | 0%

## Sprint 3
| Sprint 3 |  |  |  |  | Start | 26/05 | End | 2015-06-02
No | Task | Detail information | Implementer | Estimated hours | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Design physical diagram | DB | MinhKH | 8 | Completed | 4 | 0
2 | Design suggest page |  | MinhKH | 4 | Completed | [5 empty] | 4 | 0
3 | Design Admin dashboard | Sprint 1 Task | MinhKH | 2 | Completed |  |  |  | 0
4 | Create DB | using MySQL | MinhKH | 6 | Completed |  |  |  |  | 3 | 0
5 | Map DB - Entity |  | KhangTN | 12 | Completed |  | 8 | 4 | 0
6 | Create dao, dto |  | MinhKH | 8 | Completed |  |  | 4 | 0
7 | implement login function | include client side validation | TungTD | 10 | Waiting for Approval |  |  |  |  | 2 | 4 | 2
8 | implement register function | include client side validation | TungTD | 10 | Waiting for Approval |  |  | 2 | 4 | 4 | 0 | 0
9 | implement newsfeed page |  | TungTD | 12 | Waiting for Approval |  |  | 2 | 2 | 2 | 4 | 0
10 | real-time notification & discussion demo | notification count, left notification, real-time disscussion | KhangTN | 12 | Completed |  |  | 4 | 4 | 4 | 0
11 | store material using blob demo |  | KhangTN | 8 | Completed |  |  | 2 | 2 | 2 | 6 | 0
12 | Design Manage material |  | MinhKH | 4 | Completed | [6 empty] | 4
13
14
15
16
17
18
19
Total estimated hours
| Implementer | Total hours
| MinhKH | 32
| KhangTN | 32
| TungTD | 32
Total actual hours
| Implementer | Total hours
MinhKH
KhangTN
TungTD
| Total task | 12
| Completed task | 9
| Not completed task | 3
| Implementer | Total task | Completed task | Performance
| MinhKH | 6 | 6 | 100%
| KhangTN | 3 | 3 | 100%
| TungTD | 3 | 0 | 0%

## Sprint 4
| Sprint 4 |  |  |  |  | Start | 2015-06-03 | End | 2015-06-09
No | Task | Detail information | Implementer | Estimated hours | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Implement search function | solr | MinhKH | 16 | In process | 16 | 16 | 16 | 16 | 16 | 6 | 6
2 | Implement upload, add to folder and manage material |  | KhangTN | 16 | Waiting for Approval | 16 | 16 | 16 | 16 | 6 | 2 | 2
3 | Implement follow/unfollow teacher function |  | TungTD | 6 | Completed
4 | Implement request function |  | TungTD | 6 | Completed
5 | Implement invitation function |  | TungTD | 6 | In process
6 | Implement create class function |  | TungTD | 6 | In process
7 | Implement create post function | include article, question and material | KhangTN | 16 | Completed | 16 | 16 | 16 | 8 | 0 | 0 | 0
8 | Implement edit profile function | teacher profile, student profile | TungTD | 8 | In process
9 | Implement suggest related post function |  | MinhKH | 12 | Completed | 12 | 12 | 12 | 6 | 0 | 0 | 0
10 | design add to folder popup and create folder popup |  | MinhKH | 4 | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0
11 | component diagram |  | KhangTN | 4 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | package diagram |  | KhangTN | 4 | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0
13 | class diagram |  | MinhKH | 6 | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0
14
15
16
17
18
19
Total estimated hours
| Implementer | Total hours
| MinhKH | 38
| KhangTN | 40
| TungTD | 32
Total actual hours
| Implementer | Total hours
MinhKH
KhangTN
TungTD
| Total task | 13
| Completed task | 8
| Not completed task | 5
| Implementer | Total task | Completed task | Performance
| MinhKH | 4 | 3 | 75%
| KhangTN | 4 | 3 | 75%
| TungTD | 5 | 2 | 40%

## Sprint 5
| Sprint 5 |  |  |  |  | Start | 10/06 | End | 16/06
No | Task | Detail information | Implementer | Estimated hours | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Implement search function | Task Sprint 4 | MinhKH | 6 | In process
2 | Implement upload, add to folder and manage material | Task Sprint 4, not yet "delete" function | KhangTN | 2 | In process
3 | Implement invitation function | Task Sprint 4 | TungTD | 6 | In process
4 | Implement create class function | Task Sprint 4 | TungTD | 6 | In process
5 | Implement edit profile function | Task Sprint 4 | TungTD | 8 | In process
6 | Implement classroom page | Note: + left widget at page createPost | MinhKH | 8 | New
9 | Implement newfeeds page |  | MinhKH | 12 | New
8 | Implement manage post |  | KhangTN | 10 | New
9 | Implement reply post |  | KhangTN | 10 | New
10 | Implement accept, deny request and invitation |  | MinhKH | 8 | New
11 | Implement manage class |  | KhangTN | 12 | New
12
13
14
15
16
17
18
19
Total estimated hours
| Implementer | Total hours
| MinhKH | 34
| KhangTN | 34
| TungTD | 20
Total actual hours
| Implementer | Total hours
MinhKH
KhangTN
TungTD
| Total task | 11
| Completed task | 0
| Not completed task | 11
| Implementer | Total task | Completed task | Performance
| MinhKH | 4 |  | 0%
| KhangTN | 4 |  | 0%
| TungTD | 3 |  | 0%