## Product Backlog
No | Function | Detail | Description
1 | Autheticate | Register | Registering to become member of website
2 |  | Login/Logout | Accessing the account to use their features
3 |  | Get forgotton password | Reseting password if forgetting
4 | Edit profile |  | Users edit their profile
5 | Create class |  | Teachers create class for student's joining
6 | Create post | Create article, question, answer | User post an article, ask a question or answer a question
7 |  | Upload material | Teachers upload their studying documents
8 | Invite user | Invite teacher | Teachers invite other teachers to answer a question on
9 |  | Invite student | Teachers invite students to join the discussion in class
10 | Accept/Deny | Accept/Deny an invitation | Users accept/deny teachers' invitation
11 |  | Accept/Deny a request | Teachers accept/deny a joining request from student
12 | Track student |  | Teachers track students’ questions to see which topics a student is less known about
13 | Manage post |  | Users manage their post (edit, delete post)
14 | Manage class |  | Teachers manage students in their class
15 | Real time notify |  | System support real time notification when followed teachers have new posts or posts have new reply
16 | Real time discuss |  | New answers or replies will show at real time without refreshing page
17 | Manage learning materials |  | Students to create folders to store different kinds of studying documents
18 | Follow teacher |  | Students follow their favorite teachers
19 | Send a request |  | Students send a request to join in a teacher’s class.
20 | Suggest related post |  | System suggest related posts (related articles, related questions) for users
21 | Search |  | Users search posts or other users
22 | Manage website | Manage users | Admin can ban/unban users
23 |  | Manage psots | Admin can remove posts

## Sprint 1
Sprint 1
No | Task | Detail information | Implementer | Estimated hours | Status | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
1 | Design homepage |  | MinhKH | 10 | In process
2 | Design register page |  | ThiTD | 6 | In process
3 | Design login form | Pop-up form | ThiTD | 6 | In process
4 | Design get forget password page |  | ThiTD | 6 | In process
5 | Design student dashboard |  | TungTD | 8 | New
6 | Design teacher dashboard |  | TungTD | 8 | New
7 | Design admin dashboard |  | TungTD | 8 | New
8 | Report 1 |  | ThiTD | 4 | Completed
9 | Review report 1 |  | MinhKH | 3 | Completed
10 | Setup environment turorial |  | KhangTN | 8 | Waiting for Approval
11 | Create overall use-case |  | KhangTN | 15 | Completed
12 | Create guest use-cases | Start after KhangTN commits overall usecase | ThiTD | 10 | New
12 | Create ERD |  | MinhKH | 12 | Completed
13 | Create System Architectural Design |  | KhangTN | 10 | Waiting for Approval
14 | Report 2 |  | TungTD | 8 | New
15 | Review report 2 |  | MinhKH | 3 | New
Total estimated hours
| Implementer | Total hours
| MinhKH | 28
| KhangTN | 33
| ThiTD | 32
| TungTD | 32
Total actual hours
| Implementer | Total hours
MinhKH
KhangTN
ThiTD
TungTD